## Sheet1
TICKET #	Description	Date Created	Date Started	Work Done	Comments	Merged into Parent?	Parent Ticket				Complete
BB-1	Shift to design 1.1	03/07/22	03/08/22				master				Not Started
BB-2	make models conform to design 1.1	03/07/22	03/08/22	03/10/22		Y	BB-1				Working on it
BB-14	Create and salvage for DataEngine	03/07/22	03/08/22	03/10/22		Y	BB-1				No longer necessary
BB-3	Create and salvage for MarketManager	03/07/22	03/10/22	03/11/22		Y	BB-1
BB-4	Create and salvage for PortfolioEngine	03/07/22	03/11/22	03/13/22		Y	BB-1
BB-5	Create and salvage for AccountantManager	03/07/22					BB-1
BB-6	Create and salvage Runner	03/07/22					BB-1
BB-7	Archive old master	03/07/22					BB-1
BB-8	Create and salvage DataMarketBroker	03/07/22					BB-1
BB-9	Create and salvage MarketPortfolioBroker	03/07/22					BB-1
BB-10	Create and Salvage PortfolioAccoutantBroker	03/07/22					BB-1
BB-11	improve readme	03/08/22	03/08/22		This is probably going to be an ongoing branch – never really closed – that gets continually merged back into master / 03/08/22 ::: need to add a description fro how to use utility runner with and without file args		master
BB-12	Make a db export script, db import script	03/08/22			find out how to compress an existing mongodb, find out how to uncompress a db, probably going ot have to / Use a shell script I would imagine. Might be able to have a utility script in python		BB-13
BB-13	Create a utility runner as a seperate entity from sim runner		03/08/22	03/08/22	right now the distribution is something like “here’s a bunch of script options, tell me which to run”, / Of which, the simulation is just one of the possible utility options. I don’t like that design. I think something that / Was more of a prompt (as in, you start the utility runner, it gives you a list of utility scripts and a small description) / That takes in like a [1,4,6] meaning run scripts 1,4,6 would be a better option.	Y	BB-1
BB-15	Create a utility script to populate the DB with yahoo historical data	03/08/22	03/08/22	03/08/22		Y	BB-1
BB-16	Need basic domain model for an order	03/10/22		03/13/22	Handled in BB-4	Y	BB-3
BB-17	Move portfolio engine stuff to domain
BB-18	standaradize dto config naming conventions + validate functions
BB-19	comment all funcs
BB-20	Make tasks independent repo
BB-21	make requests automatically independent threads for callback
BB-22	make sure thread time for sending order is actually just “has this time passed”
BB-23	Make all the new engines mesh with each other